## Slide 1: Window production process flow

## Slide 2: OPERATING STEPS
Quotes & Contract
Technical drawing
Execution plan and PGD* of the prototype
Prototype manufacturing and delivery
Location plans adn PGD of the whole project
Execution plan
Update of the quotation according to the validated plans
Manufacturing and delivery on the site
*PGD : Detailed General Project

## Slide 3: Quote & Contract (Quotation submission upon receipt of a request for quotation)
Requirement :
  1. Qualification of the customer request and transmission of the complete consultation file (DPGF, nomenclature, CCTP, thermal and acoustic notices, graphic parts,..)
  2. Quotation validation and preparation of contract documents
Responsible :
  Mr. Mehmet KONAK (Deputy director)
  Mrs. Fatma ALKAN (Pricing engineer)
  Mr. Camille SEN (Business Manager)
Deadline :
  10 working days (quote)
  7 working days (preparation of contract documents)

## Slide 4: Technical drawing
Before presenting all the typologies of the project, we choose the most common typology of the project (or the one chosen by the customer) and we begin the study of the details of execution on this window.
Requirement :
  Signature of DC4 and send the copy of the contract
Responsible :
  Mr. Toufik HADJENE (Execution study manager)
Deadline :
  7 working days (1st diffusion)

## Slide 5: Execution plan and PGD of the prototype
We are preparing the General Detailed Project (PGD, see next slide) of the prototype. We ask that you carefully review the PGD to transmit the latest changes if necessary. Once the PGD of the prototype has been validated, we will proceed with the execution of the plan.
Requirement :
  Approval of technical drawings
Responsible :
  Mr. Toufik HADJENE (Execution study manager)
Deadline :
  3 working days for PGD (1st diffusion)
  4 working days for prototype plan (1st diffusion)

## Slide 6
The PGD is a document in which all the properties of the window are described (direction of opening, accessories, characteristics of the glazing, acoustic and thermal constraints,...).

## Slide 7: Prototype manufacturing and delivery
We produce the prototype and deliver to the site.
Requirement :
  Approval of protoype plan
Responsible :
  Mr. Mertcan MUNGEN (Civil engineer)
  Mr. Gökay AYTER (Construction responsible)
Deadline :
  5-6 weeks of manufacture
  9-10 delivery days (for 1-4 products)

## Slide 8: Localisation plans and PGD of the whole project
Preparation of location plans of all typologies and the PGD file for the whole project. Following the validation of these location plans, the PGD will be prepared and submitted for validation.
Requirement :
  Receipt of location plans and other necessary documents.
Responsible :
  Mr. Toufik HADJENE (Execution study manager)
Deadline :
  7 working days (1st diffusion)

## Slide 9: Execution plan
We draw up the execution plans for the windows, taking into account the PGD and the location plans.
Requirement :
  Approval of location plans and the PGD
  Receipt of updated plans for execution (DCEEXE)
Responsible :
  Mr. Toufik HADJENE (Execution study manager)
Deadline :
  3 weeks (1st diffusion)
    Each revision requested +1 week on these deadlines
    These study deadlines are stated on the condition of having a return within 15 days maximum

## Slide 10: Update of the quotation according to the validated plans
After clarification of the requests of the architect and the construction site, a comparison with our initial offer will be made to determine the inconsistencies.
Requirement :
  Approval of execution plans and validation of supplementary requests
Responsible :
  Mrs. Fatma ALKAN (Pricing engineer)
  Mr. Camille SEN (Business manager)
Deadline :
  5 working days

## Slide 11: Manufacturing and delivery
We start the manufacturing process according to validated plans and PGD.
Requirement :
  Approval of execution plans by signing and sealing
Responsible :
  Mr. Mertcan MUNGEN (Civil engineer)
  Mr. Gökay AYTER (Construction responsible)
Deadline :
  15 weeks of manufacture for the first series of 50-60 windows (according to size)
  9-10 working days for delivery
  Following delivery every 2 weeks